# Invitation to Tender

| Tender Name: Final Ecosystem Impact Review and Program Evaluation |  | Tender No: MC-AFA/NBO/034/ 2020 |
| --- | --- | --- |
| Location: Nairobi, Kenya | Correspondence Language(s): English |  |
| Brief Summary Description of Project: Mercy Corps AgriFin Program is seeking for a firm to conduct a final ecosystem review and program evaluation |  |  |

| Tender Package Available from: 20th July 2020 | Tender Package Pickup Location: www.mercycorpsagrifin.org , https://www.mercycorps.org/tender or Interested bidders can submit a request for the tender documents to this email address ‘agrifinprocurement@mercycorps.org |
| --- | --- |
| Deadline for Offer Submission: 7th August 2020 | Submit Offers to: The Tender box at Mercy Corps Kenya ABC Place, Block A, 3rd floor OR Via Email to: tenders@mercycorps.org |

Mercy Corps reserves the right to accept or reject any late offers

| Questions and Answers (Q&A) |  |
| --- | --- |
| If any, Submit Questions in writing to: www.mercycorpsagrifin.org or https://www.mercycorps.org/tender |  |
| Last Day for Questions: 24th July 2020 | Questions will be answered by: 28th July 2020 |
| Questions will be answered through: All prospective bidders will access consolidated questions and answers on these websites https://www.mercycorps.org/tender andwww.mercycorpsagrifin.org by 28th July 2020 at 5.00 PM pacific time |  |

| Documentation Checklist |  |
| --- | --- |
| These documents are contained within this tender package: | - Invitation to Tender - General Conditions for Tender - Criteria and Submittals - Price Offer Sheet - Supplier Information Form - Scope of Work - Sample Contract |

# General Conditions for Tender

Mercy Corps invites proposals for the goods, services and/or works described and summarized in these documents, and in accordance with procedures, conditions and contract terms presented herein. Mercy Corps reserves the right to vary the quantity of work/materials specified in the Tender Package without any changes in unit price or other terms and conditions and to accept or reject any, all, or part of submitted offers.

2.1	Mercy Corps’ Anti-Bribery and Anti-Corruption Statement

Mercy Corps strictly prohibits:

- Any form of bribe or kickback in relation to its activities

This prohibition includes any request from any Mercy Corps employee, consultant or agent for anything of value from any company or individual in exchange for the employee, consultant or agents taking or not taking any action related to the award of a contract or the contract once awarded.  It also applies to any offer from any company or individual to provide anything of value to any Mercy Corps employee, consultant or agent in exchange for that person taking or not taking any action related to the award of the contract or the contract.

- Conflicts of interests in the awarding or management of contracts

If a company is owned by, whether directly or indirectly, in whole or in part, any Mercy Corps employee or any person who is related to a Mercy Corps employee, the company must ensure that it and the employee disclose the relationship as part of or prior to submitting the offer.

- The sharing or obtaining of confidential information

Mercy Corps prohibits its employees from sharing, and any offerors from obtaining, confidential information related to this solicitation, including information regarding Mercy Corps’ price estimates, competing offerors or competing offers, etc.  Any information provided to one offeror must be provided to all other offerors.

- Collusion between/among offerors

Mercy Corps requires fair and open competition for this solicitation.  No two (or more) companies submitting proposals can be owned or controlled by the same individual(s). Companies submitting offers cannot share prices or other offer information or take any other action intended to pre-determine which company will win the solicitation and what price will be paid.

Violations of these prohibitions, along with all evidence of such violations, should be reported to:

integrityhotline@mercycorps.org

Mercy Corps will investigate allegations fully and will take appropriate action.  Any company, or individual that participates in any of the above prohibited conduct, will have its actions reported to the appropriate authorities, will be investigated fully, will have its offer rejected and/or contract terminated, and will not be eligible for future contracts with Mercy Corps. Employees participating in such conduct will have his/her employment terminated.

Violations will also be reported to Mercy Corps’ donors, who may also choose to investigate and debar or suspend companies and their owners from receiving any contract that is funded in part by the donor, whether the contract is with Mercy Corps or any other entity.

2.2 	Tender Basis:

- All offers shall be made in accordance with these instructions, and all documents requested should be furnished, including any required (but not limited to) supplier-specific information, technical specifications, drawings, bill of quantities, and/or delivery schedule. If any requested document is not furnished, a reason should be given for its omission in an exception sheet.

- No respondent should add, omit or change any item, term or condition herein.

- If suppliers have any additional requests and conditions, these shall be stipulated in an exception sheet.

- Each offeror may make one response only.

- Each offer shall be valid for the period of 180 days from its date of submission.

- All offers should indicate whether they include taxes, compulsory payments, levies and/or duties, including VAT, if applicable.

- Suppliers should ensure that financial offers are devoid of calculation errors. If errors are identified during the evaluation process, the unit price will prevail. If there is ambiguity on the unit price, the Selection Committee may decide to disqualify the offer.

- Any requests for clarifications regarding the project that are not addressed in written documents must be presented to Mercy Corps in writing. The answer to any question raised in writing by any offeror will be issued to that offeror. In some cases Mercy Corps may choose to issue clarifications to all offerors. It is a condition of this tender that no clarification shall be deemed to supersede, contradict, add to or detract from the conditions hereof, unless made in writing as an Addendum to Tender and signed by Mercy Corps or its designated representative.

- This Tender does not obligate Mercy Corps to execute a contract nor does it commit Mercy Corps to pay any costs incurred in the preparation and submission of proposals. Furthermore, Mercy Corps reserves the right to reject any and all proposals, if such action is considered to be in the best interest of Mercy Corps.

2.3 	Supplier Eligibility

Suppliers may not apply, and will be rejected as ineligible, if they:

- Are not registered companies

- Are bankrupt or in the process of going bankrupt

- Have been  convicted of illegal/corrupt activities, and/or unprofessional conduct

- Have been guilty of grave professional misconduct

- Have not fulfilled obligations related to payment of social security and taxes

- Are guilty of serious misinterpretation in supplying information

- Are in violation of the policies outlined in Mercy Corps Anti Bribery or Anti-Corruption Statement

- Supplier (or supplier’s principals) are on any list of sanctioned parties issued by; or are presently excluded or disqualified from participation in this transaction by: the United States Government or United Nations by the United States Government, the United Kingdom, the European Union, the United Nations, other national governments, or public international organizations.

Additional eligibility criteria, if applicable, are stated in section 3.2 of this tender package.

2.4   	Response Documents

Offerors can either utilize the response documents contained in this tender package to submit their offer or they can submit an offer in their own format as long as it contains all the required documents and information specified by this tender.

2.5	Acceptance of Successful Response

Documentation submitted by offerors will be verified by Mercy Corps. The winning offeror will be required to sign a contract for the stated, agreed upon amount.

2.6	Certification Regarding Terrorism

It is Mercy Corps’ policy to comply with humanitarian principles and the laws and regulations of the United States, the European Union, the United Nations, the United Kingdom, host nations, and other applicable donors concerning transactions with or support to individuals or entities that have engaged in fraud, waste, abuse, human trafficking, corruption, or terrorist activity. These laws and regulations prohibit Mercy Corps from transacting with or providing support to any individuals or entities that are the subject of government sanctions, donor rules, or laws prohibiting transactions or support to such parties.

# Criteria & Submittals

3.1 Contract Terms Mercy Corps intends to issue a Fixed Price contract to one or several company(ies) or organization(s). The successful offeror(s) shall be required to adhere to the statement of work and terms and conditions of the resulting contract. The anticipated contract is incorporated in Section 6 herein. By submitting an offer, offerors certify that they understand and agree to all of the terms and clauses contained in Section 6.

3.2 Specific Eligibility Criteria Eligibility criteria must be met and the corresponding supporting documents listed below under “Tender Submittals” must be submitted with offers. Offeror who do not submit these documents may be disqualified from any further technical or financial evaluation. Eligibility Criteria: - The firm must be an eligible business under the applicable laws and regulations in their countries of operations - The firm must be in good standing with the taxation or legal authorities - The firm must have a satisfactory record of performance and business ethics based on information available to Mercy Corps

3.3 Tender Submittals Documents and required information listed in tender submittals are necessary in order to support the eligibility criteria and to conduct technical evaluations of received offers (and due diligence). While absence of these documents and/or information does not denote mandatory disqualification of suppliers, the lack of these items has the potential to severely and negatively impact the technical evaluation of an offer. Documents supporting the Eligibility Criteria: - Business Registration Documents - Articles /Memorandum of Association - Tax registration and Compliance documents - Three References from previous work projects (including contact information) Documents to conduct the Technical Evaluation and additional Due Diligence: - Company Profile, 2-page max - Evidence of similar services offered (including contact information, contract value, and geographic locations) - Detailed Proposal and CVs of technical staff including their role, qualification and experience - Portfolio of work - Financial offer Price Offer : The Price offer is used to determine which offer represents the best value and serves as a basis of negotiation before award of a contract. As a Fixed-Price contract, the price of the contract to be awarded will be an all-inclusive fixed price basis, either in the form of a total fixed price or a per-unit/deliverable fixed price. No profit, fees, taxes, or additional costs can be added after contract signing. Offerors must show unit prices, quantities, and total price, as displayed in the Offer Sheet in Section 4. All items must be clearly labeled and included in the total offered price. Offerors must include VAT and customs duties if applicable in their offer.

3.4 Currency Offers should be submitted in: USD Payments will be made in: USD

3.5 Tender Evaluation (Trade-Off Selection Method) Based on the above submittals, a Mercy Corps Tender Committee will conduct a tender evaluation process. Mercy Corps reserves the right to accept or reject any or all proposals, and to accept the offer(s) deemed to be in the best interest of Mercy Corps. MC will not be responsible for or pay for any expenses or losses which may be incurred by any Offeror in the preparation of their tender. Evaluations will be conducted as described in the following subsections:

3.5.1 Scoring Evaluation Trade-Off Method Mercy Corps Tender Committee will conduct a technical evaluation which will grade technical criteria on a weighted basis (each criteria is given a percentage, all together equaling 100%). Offeror's proposals should consist of all required technical submittals so a Mercy Corps committee can thoroughly evaluate the technical criteria listed herein and assign points based on the strength of a technical submission. Award criteria shall be based on the proposal’s overall “value for money” (quality, cost, delivery time, etc.) while taking into consideration donor and internal requirements and regulations. Each individual criteria has been assigned a weighting prior to the release of this tender based on its importance to Mercy Corps in this process. Offeror(s) with the best score will be accepted as the winning offeror(s), assuming the price is deemed fair and reasonable and subject to the additional due diligence in section 3.5.2. When performing the Scoring Evaluation, the Mercy Corps tender committee will assign points for each criteria based on the following scale: Point; Rationale. 0; Not acceptable; has not met any part of the specified criteria. 1-4; Has met only some minimum requirements and may not be acceptable. 5; Acceptable. 6-9; Acceptable; has met all requirements and exceeds some. 10; Acceptable; has exceeded all requirements. Evaluation Criteria; Weight (%); Possible Points (1 to 10); Weighted Score. (A); (B); (A*B). Methodology. The proposal outlines an approach that is tailored to achieving the objectives of the assignment; 10%. The proposal indicates commitment to quality of data collected; 10%. The proposal indicates analysis procedures that are to be used in developing the insights; 10%. The proposal is in line with the expected timelines for delivering the project; 10%. Team Knowledge and Experience. The proposal firm/consultant has the necessary qualifications to conduct the assignment; 10%. The firm/consultant have the necessary project experience to execute the work; 10%. The firm/consultant has proof of handling projects with similar budgets before indicating capacity and ability; 10%. Unique qualifications. The firm/Consultants work, objectives and unique qualifications convey a positive feeling of which lays the foundation for a trusted relationship.; 5%. Value added services. It is evident that the firm has the necessary capacity to provide other services beyond the current engagement; 5%. Cost of the proposal and terms of payment. The pricing is well documented, with the preferred payment schedule and is within the budget; 5%. The proposal addresses all items requested by us whether verbally, electronically or in the TOR; 5%. The proposed fee is reasonable based on the experience, unique value and knowledge the firm brings to the engagement.; 10%. TOTAL POSSIBLE SCORE:; 100%.

3.5.2 Additional Due Diligence Upon completion of both the technical and financial evaluations Mercy Corps may choose to engage in additional due diligence processes with a particular supplier or supplier(s). The purpose of these processes is to ensure that Mercy Corps engages with reputable, ethical, responsible Suppliers with solid financials and the ability to fulfill the contract. Additional due diligence may take the form of the following processes (though it is not limited to): - Reference Checks

# Offer Form

Offerors must submit their own independent offer including at least (but not limited to): - All documents requested in the “Eligibility Criteria” section of this Tender Package - All documents requested in the “Tender Submittals” section of this Tender Package - All information listed in the “Documents Comprising the Proposal” section below All offers must be duly signed (including position and full name of the signer) and stamped, with the date of completion.

Documents Comprising the Proposal

The following information must be included in the offer of any potential offeror:

- Cover Letter explaining interest to be a contracted vendor or supplier, and the details of the Proposal. The content of the cover letter shall include the following information:

- A Price Offer detailing the unit price only, using the Price Offer Sheet template provided in section 7 or your own price sheet with the daily rate for key personnel  and expenses indicated.

- Completed and signed Mercy Corps Supplier Information Form (template provided in section 7)

- Other important documents offeror feels need to be attached to support their proposal

The original proposal shall be signed by the offeror or a person or persons duly authorized to bind the offeror to the contract. Financial offer pages of the proposal shall be initialed by the person or persons signing the proposal and stamped with the company seal.

Any interlineations, erasures, or overwriting shall be valid only if they are initialed by the person or persons signing the proposal.

# 5. Scope of Work/Technical Specifications

Mercy Corps Background

Mercy Corps is a leading global organization powered by the belief that a better world is possible. In disaster, in hardship, in more than 40 countries around the world, we partner to put bold solutions into action—helping people triumph over adversity and build stronger communities from within. Now, and for the future. As a global organization with programs in over 40 countries, we focus much of our advocacy on influencing governments, multi-lateral institutions as well as foundations and the private sector to improve relevant policies, practices and decisions in order to better help vulnerable communities lift themselves out of poverty.

Mercy Corps AgriFin

Mercy Corps’ mission is to alleviate suffering, poverty and oppression by helping people build secure, productive and just communities. The AgriFin Accelerate (AFA) program is a six year, USD 24.7 million program of Mercy Corps, supported by The MasterCard Foundation.

The core problem AgriFin Accelerate seeks to address is the inclusion gap for smallholder farmers (SHF) who lack access to affordable, accessible, demand-driven financial products and services that drive higher productivity and income for farm families.

Drawing on Mercy Corps’ experience implementing the AgriFin Mobile program and years of work in the agriculture, finance and ICT sectors, AgriFin Accelerate will support the expansion of digital financial services (DFS) to one million farmers in Sub-Saharan Africa (SSA) over six years, delivered by growing ecosystems of diverse service providers. AgriFin Accelerate’s primary target group is unbanked smallholder farmers living on less than $2 per day in Kenya, Tanzania and Zambia.

Three outcomes will contribute to the achievement of this goal:

- Outcome 1: Market actors expand, improve and continue to offer high-impact DFS products and services that are tailored to address the expressed needs of SHFs;

- Outcome 2: Farmers increase capability to access and utilize demand-driven, high impact technology-enabled financial products and services relevant to SHFs;

- Outcome 3: Ecosystems around both supplier and farmers emerge supporting provision of digital financial and informational services to SHFs that are used at scale.

The core activity of this program is to build technical partnerships among high quality service providers to reach smallholder farmers with critical products and services through mobile and other digital channels, using a rapid prototyping and iterative design approach. These providers encompass a wide range of institutional types, including banks, agricultural extension providers, farmer associations, MFIs, mobile network operators and others. A key element of the program is the ability to create viable business models and necessary technical interfaces between partners to build “bundles” of services for farmers on unified platforms, therefore building the relevance and value proposition of mobile-based services to promote mass uptake.   This activity is kicked off with in depth ecosystem research and ongoing research in the forms of annual farmer benchmarks and focuses on four areas for innovation:

  - Products and services for farmers;

  - Delivery channels to reach farmers;

  - Incorporation and support for technology companies working to disrupt agriculture and serve farmers; and

  - Use cases of alternative data to support farmer access to services.  The program has 4-5 prioritized value chains in each country, but has also worked in alternate agricultural Value Chains.

The second activity area addresses barriers to effective adoption of services where farmers lack knowledge and capability to utilize new technology, products, services and channels. DFS providers typically struggle with a lack of proven, effective tools, channels and viable models to build SHF capacity. This activity is supported by initial ecosystem research and annual farmer benchmark studies in each country and has had a special emphasis on reaching women and youth farmers through the AFA Digital Farmer Capability Lab based in the Hub office in Nairobi. The Lab, which ran from 2015 to 2018, targeted qualified partners and worked with them to develop and test SHF capability tools and sustainable delivery approaches linked to ongoing product and channel development activities from Output 1, establishing proof points around impact for SHF and viability for providers.

The third activity relates to use of program learning to drive ecosystem growth. Market ecosystem actors and the development community lack sufficient information, proven products and tools, and effective partnership models to successfully provide digital financial services to farmers. The program is designed to serve as a public information resource related to digitally-enabled services for smallholder farmers, sharing program research, impact evaluations, tools and project engagement learning, as well as convening stakeholders and disseminating lessons learned through newsletters, a dedicated website and social media. Following the learning agenda, the program seeks to contribute toward the development of good practice and practical tools to develop mobile-enabled services for SHF.

The AFA program launched in March 2015 in Kenya with a phased approach to opening new country programming, allowing for the Kenya hub office to establish the model and core matrix team meant to serve all three countries over the life of the program. Program outreach targets include the lead indicator to support expanded provision of DFS services to 1 million smallholder farmers (SHF) for the program over the six-year program span with Kenya at 500,000 SHF, Tanzania at 350,000 SHF & Zambia at 150,000, linked to rollout of country programming and maturity of ecosystem partners around DFS smallholders.  We work to achieve this target by working with carefully selected partners and implementing joint “innovation” engagements on a cost-share basis to promote farmer-centric solution development, prototyping, testing and scale.

Initial ecosystem evaluations are conducted to kick off each country program, providing strategic direction for our technical approach and partnership strategies.  The Kenya ecosystem study was completed by July 2015 and first engagements were launched in August 2015. The Tanzania ecosystem study was completed by February 2016 and first engagements were launched in February 2016, with formal program launch in July 2016. The Zambia ecosystem study was concluded in January 2017 and the program officially launched in February 2017. To date, 176 partner engagements have been completed across the three countries, with the following breakdown by country and information on live engagements and engagements in development:

|  | Engagement Activity |  |  |  |
| --- | --- | --- | --- | --- |
|  | Completed | Ongoing | Preparation | TOTAL |
| Kenya | 67 | 2 | 12 | 81 |
| Tanzania | 55 | 0 | 5 | 60 |
| Zambia | 34 | 1 | 0 | 35 |
| TOTAL | 156 | 3 | 17 | 176 |

The size and scope of engagements varies considerably, with procurement values between zero and $500,000 and duration of one month to one year.  AFA works with partners in two main categories, including “core” DFS platform providers (ex. Safaricom, Equity Bank, Cooperative Bank, Halotel, Zoona) and value-added service provider (VAS) partners (ex. iProcure, Arifu, FarmDrive, Mediae) which serve the purpose of aggregating farmers and providing complementary services enabling DFS and increasing productivity and income gains among farmers.  Some engagements involve multiple partners, while others focus on a sole partner.  The breakdown of partners actively engaged through AFA is presented below:

|  | AFA PARTNERS |  |  |
| --- | --- | --- | --- |
|  | CORE | VAS | TOTAL |
| Kenya | 28 | 53 | 81 |
| Tanzania | 13 | 22 | 35 |
| Zambia | 14 | 22 | 36 |
| TOTAL | 55 | 97 | 152 |

To complement partner engagements, approximately one third of the AFA program budget is dedicated to strategic learning and sharing lessons learned with the broader ecosystem through research, publications, events, social media engagement and ecosystem collaboration with organizations including CGAP, FSD programs in all countries, UNCDF and others. This study will build onto the continued effort to show some level of causality between learning and changes / program outcomes at the institution and ecosystem level.

In particular, there is increased importance for the project to show impact at the ecosystem level to note the increased number of AFA partners and their peers in the agri-fin-tech ecosystem, who have entered the realm of serving smallholder farmers with digital financial and information products. Across the range of digitally-enabled products and services, the directionality of cause and effect of change in the ecosystem is difficult to prove and thus attribute. Making this crucial link is an imperative towards evaluating the program’s impact.

Purpose of Engagement

This final program evaluation is being commissioned by the Mercy Corps AgriFin Accelerate program, which will work in collaboration with the MasterCard Foundation throughout the evaluation process. The evaluation will serve as a final program evaluation of the programs since inception, incorporating ecosystem impact evaluation as well as fulfillment of program milestones and objectives. The evaluation should provide both the Mastercard Foundation and Mercy Corps an understanding of progress towards project objectives from inception to program closure, with a focus on progressing from the mid-term evaluation of the program that was completed in February 2018, and the Kenya, Tanzania and Zambia ecosystem studies that revealed the status upon program launch across agricultural, digital, and solutions landscapes in these countries at the baseline point. It is expected that the contents of the evaluation will allow for a review of program design, achievements, and challenges in order to generate key lessons for future strategic and programming decisions related to the AgriFin Accelerate program, the overall MasterCard Foundation portfolio learnings and the smallholder financial and digital inclusion sector more broadly.

The AgriFin Accelerate (AFA) program seeks to influence change at the client (farmer) level, institutional level and the ecosystem level, as represented in the below summary of its TOC (theory of change):

If well-designed and accessible digital financial services are bundled with productivity tools and offered to smallholders and digital ecosystems are accelerated to effectively provide relevant services to smallholder farmers at scale, then financial inclusion will increase, driving gains for farmer income and productivity.

Figure 1. Mercy Corps AFA Results Framework

Based on the AFA Theory of Change and results framework, the final evaluation should measure progress against completion of program milestones and objectives, as well as at the three expected levels of impact at farmer, partner and ecosystem levels. The program has commissioned a range of separate impact assessment that prioritize impact and learnings at the client and partner levels, hence client level impacts need not be measured in this current scope of work but should be drawn on for final reporting in this scope. The final evaluation will engage actively against the AFA learning agenda and results framework in order to directly measure change (i.e. outputs and available outcomes) across institution and ecosystem levels. Depending on available data and the maturity of the project, the evaluation may prioritize a smaller set of learning questions to narrow the evaluation scope.  Client, Institution and Ecosystem-level AFA learning questions include:

Client (Farmer) – How does a platform approach (DFS/e-Commerce) enable scaling of digital financial and value-added services for farmers?

- What impacts have AFA partners had on SHFs income, productivity and resilience to shocks?

- What financial and value-added products and services do SHFs, including women and youth value most and why?

- How does bundling of products or services impact uptake and usage of Digital Financial Services?

- What capability tools have the highest impact on SHF willingness and ability to use Digital Financial Services?

- What distribution channels are most effective for delivery of digital services to SHFs?

- What other complementary services are needed to break or address critical barriers to farm-level investment, efficiency and productivity growth?

Institution – Service providers expand, improve and scale up offering digital financial and information services tailored to the needs of SHFs:

- What has been the outcome of engagement with the AgriFin Accelerate program at the institutional level (e.g. number and diversity of new services increases, Innovation in models, products and channels increases, technical scope and reach of new services increases)?

- How well has the AgriFin Accelerate program worked to understand and align objectives with partner institutions?

- Where have institutions derived the most value from collaboration with the AgriFin Accelerate team? Where have there been challenges?

- Has engagement with the AgriFin Accelerate team changed how institutions understand and engage with smallholder farmers, and with other ecosystem partners? If so then how?

- How effectively has the program driven partnerships between diverse institutions with the aligned objective to better serve smallholder farmers?

- How relevant do institutions think the bundled services developed in collaboration with the AgriFin Accelerate team are to different market segments (e.g. women, youth)?

- How effectively has the program integrated new processes for iterative design with partner institutions? Were institutions actively engaged in the design process? Have partner institutions on-boarded client-centric design processes into their product development cycle and internal KPI performance metrics?

- How much value have partner institutions derived from AgriFin Accelerate’s events and convenings?

- How has the due diligence process contributed to success in product quality and go to market and technical strategies?

Ecosystem – Emergence of ecosystems with favorable rules, incentive and networked actors supports digital solutions to SHFs:

- How has the ecosystem benefited from the AgriFin Accelerate program (e.g. new insights on SHFs, more sophisticated learnings, crowding-in of new players)?

- What ecosystem features are most important for success and expansion of digital solutions for agriculture? What are the key barriers towards growth and expansion?

- How has the program utilized market intelligence, technical convenings, dissemination and partnerships to help to shape the ecosystem featured and “crowd in” activity in the space?

- How effectively has the program worked to catalyze investment in DFS focused on smallholder farmers at the ecosystem level?

- How effectively has the program fostered collaboration between divergent players in the market to offer bundled services or to develop a more conducive ecosystem?

- What new models and solutions have developed as a result of diverse players collaborating under this program?

- How effectively has the program identified and addressed systemic challenges to market growth? In which markets has the team been more successful in innovating to address these failures? What other levers or interventions are needed and which type organizations are best placed to intervene?

- To what extent are program learnings and tools being disseminated to and utilized by key ecosystem players? What impact is the program’s learning having on the development of the ecosystem?

- How does ecosystem engagement and outcomes differ across markets in which it engages?

Scope of Work

Mercy Corps requires the services of a research firm with extensive experience designing, and implementing high caliber program evaluations, including ecosystem studies, to conduct an end-line impact evaluation of the AFA program, in order to provide a final evaluation of program performance, answering specific program learning questions at the farmer, partner and ecosystem levels. As part of this engagement, the consultants will be expected to conduct the below activities:

To complete the AFA final program evaluation, the selected evaluator should propose a framework / methodology that includes:

- A mixed-methods approach including quantitative and qualitative data sources. Our emphasis is on the reliability and validity of information and analysis, rather than a preference for a specific data type or collection approach;

- Primary data collection with key stakeholder groups at the partner and ecosystem levels. The MasterCard Foundation values active and meaningful participation of program stakeholders in the evaluation, as well as creative means of communicating evaluation results back to stakeholders at multiple levels;

- A global overview, with a geographic focus of Kenya, Tanzania and Zambia, as key areas of influence and impact, with a view to regional impacts where possible;

- At the partner level, research that measures:

  - the intended and unintended consequences of AFA-led or supported interventions across partner engagements (i.e. product, plans, projects, outreach, strategy, partnerships and learnings) and any changes invoked by those interventions; and

  - how program partners have been influenced by AFA program learnings;

- At the ecosystem level, research guided by the initial ecosystem studies, assess the current condition of the environment to support digitally-enabled service provision to smallholder farmers, indicating any changes in the environment where the AFA program has contributed toward the growth and change in ecosystems, as well as clearly indicating which problems still exist;

- To build on the work being done on the ecosystem studies, the research should incorporate Social Network Analysis (SNA) to enrich output from previous ecosystem studies to:

  - Better understand the differentiated roles played by different actors in the AgriFin stakeholder ecosystem, during and after innovation processes

  - Better understand the impact pathways created when change in one stakeholder or group of stakeholders, triggers impact across other domains of the ecosystem

  - Validate stakeholders’ views on actors’ relationships already established by existing program learnings and case studies

  - Understand how other actors (outside of program partners) are influenced by AFA program learnings

- Where feasible, measure return of investment and other business viability metrics and KPIs as appropriate to understand impacts at AFA partner levels.

- The evaluator should consolidate evidence of separate impact evaluations at the farmer level across AFA partners, including those directly completed by AFA and also by third parties under separate funding where deemed appropriate and agreed with AFA management. The evaluators should draw conclusions on the program’s impact at the farmer level, including around gender, based on these studies and present in this study, including facets of impact such as active use of services, gender and other elements linked to the AFA learning agenda;

- Where possible, the evaluator should include an evaluation of the potential for youth farmer inclusion and youth job creation in rural areas, which is the current strategic focus for the MasterCard Foundation and which has been touched on tangentially by some AFA activities;

- Other activities, as agreed with the AFA management team and the MasterCard Foundation with the consultants, as related to the AFA impact and learning agenda.

Deliverables

The consultant will work to produce and support production of the following deliverables, in close collaboration with AgriFin teams and relevant partners:

- Final Ecosystem Impact Review & Program Evaluation Inception Report: In the inception phase of the evaluation, the evaluator is expected to review the available documentation for the evaluation and prepare an Inception Report/Work Plan. The report should not exceed thirty (30) pages and should include the following elements:

  - Overview of project

  - Purpose of the Evaluation

  - Evaluation Framework / Key Questions

  - Evaluation Approach and Methods, including data collection and analysis. Draft data collection tools including any surveys and interview protocols, should be included in the appendices to the report

  - Data analysis plan, addressing how the primary and secondary data will be systematically analyzed to address the learning questions

  - Activities and timeline, including roles and responsibilities of all team members

Timely feedback on the inception report will be provided by AFA and the Mastercard Foundation; a final revised version of the Inception Report must be approved before the evaluation proceeds.

- Final Ecosystem Impact Review & Program Evaluation Report; The draft evaluation report should not exceed fifty (50) pages and should include the following sections:

  - Executive Summary (maximum two pages)

  - Project introduction/background

  - Evaluation Purpose, including evaluation framework/learning questions

  - Evaluation approach and methodology, including limitations

  - Findings, organized in a clear and logical fashion that corresponds to the evaluation questions, assessment criteria, and overall project.

  - Conclusions

  - Recommendations

Annexes to the report (independent of document page count) should include:

- Terms of Reference for the evaluation

- Any further supporting information on the methodology, including individuals/groups consulted, documents reviewed, compiled monitoring data, etc.

The Consultant may be asked to present the draft report in person to Mercy Corps AFA in Nairobi. Timely feedback on the draft report will be provided by AFA and the Mastercard Foundation.

- Evaluation Updates: In addition to these deliverables, the evaluator will engage in regular briefing updates – either by phone or by email – with Mercy Corps and The MasterCard Foundation.

- All other related work product: All materials related to this evaluation, including evaluation insights should already be incorporated in the final evaluation report, but separate documents may be submitted to provide the full body of work on the evaluation.

# 6. Sample Contract

This is the anticipated contract. However, if required, additional terms and conditions may be added by Mercy Corps in the final contract.

# 7. Attachments to the Tender Package