Scope of Work

Firm or Individual:	Firm

Program:  	GIZ Digital Agriculture Africa (DAA) Project

Scope of Project:	Business and sustainability model for Sprout

Country:		Regional

From:			January 9, 2023

To:			March 15, 2023

Task Manager:	 D-CSA and Sprout Lead

Technical Support:         Sprout Product Lead, 
                                           Mercy Corps AgriFin Program Director.

Program Context

Nearly one and a half billion poor people live on less than US$1.25 a day. One billion of them live in rural areas where agriculture is their main source of livelihood. An estimated 70 million Smallholder Farmers (SHF) live in Sub Saharan Africa, over half of whom are women. Smallholders, who typically farm two hectares or less, provide over 80% of the food consumed in a large part of the developing world, contributing significantly to poverty reduction and food security. However, ever increasing fragmentation of landholdings, especially in infrastructure, coupled with reduced investment support, growing competition for land and water, rising input prices and climate change threaten this contribution, leaving many smallholders increasingly vulnerable.

Transformational Potential of Agriculture

Agriculture has been found to play a powerful role in poverty reduction, especially when agricultural development has focused on small farms grow. It is estimated that a 1% increase in crop productivity reduces the number of poor people by 0.72% in Africa.

Given increasing world populations and demand for food, SHFs occupy an important segment of the global agricultural value chain. Multinational buyers will increasingly rely on smallholders to secure their supply of commodities and to help satisfy consumer sustainability preferences. At an estimated $450 billion, the global demand for smallholder agricultural finance is large—and largely unmet. Credit provided by informal and formal financial institutions, as well as value chain actors, currently only meets an estimated USD 50 billion of the more than USD 200 billion need for smallholder finance in the regions of sub-Saharan Africa, Latin America, and South and Southeast Asia. Impact driven smallholder agricultural lenders, such as Root Capital in Kenya and elsewhere, currently satisfy less than two percent of the demand.  The volume and value of savings, lending and payment transaction SHFs in most African countries is not specifically measured.

Mobile phones are a powerful tool to access the electronic national retail payments system and enable vast numbers of clients to use a range of financial and informational services at lower cost. In agriculture, progressively more services are being delivered via mobile phone. Applications now deliver direct specific, timely information on agricultural production methods to farmers through their mobile phones. Moving beyond in person communication, there are internet- and SMS-based services that allows farmers to access inputs; access price information on different crops and provides a platform for smallholders to collectively sell crops and buy inputs, thereby lowering costs and accessing new markets.

Empirical evidence shows that digital innovation can revolutionize the way smallholder farmers feed the world, that’s why, based on years of learning and iterating, we built the AgriFin model to facilitate that process.

Launched in 2012, AgriFin’s primary target group is un-banked smallholder farmers living on less than USD 2 per day. Mobilizing a vast network of partners, AgriFin ensures that the needs of farmers inform the design of partner products and services. Our shared global context is challenging – climate variability and population growth present unprecedented challenges. Yet, our experience tells us that farmers are determined to beat the odds.

With access to the right tools, smallholder farmers can build the resilience they need against climate and emergency shocks, and continue to feed their communities. We know that government and private sector partners are best suited to deliver those tools, and that technology is a critical accelerator. Our aim is to connect smallholder farmers to products and services that increase their productivity and income by 50%, with a 40% target population of Women and Youth.

Program Overview: GIZ #SmartDevelopmentFund

The challenges in agriculture in Africa, particularly for the smallholder farmers producing 80% of its food for consumption, are complex, and no single solution exists to reverse age-old issues around markets, infrastructure, poverty and exclusion. Digital solutions can provide relatively low-cost solutions that reach scale quickly, open new markets, and surpass the traditional brick-and-mortar approach to customer acquisition and the distribution and sales of products and services.  Over the past five years, AgriFin has worked both to build capacity of fintech and agritech innovators to scale and also worked to broker partnerships for them onto larger digital platforms, typically hosted by banks, mobile network operators, large agricultural enterprises and government. Digital platforms are evolving as drivers for impact and viability in delivery of key services for agriculture and also for scale up of young, breakthrough technology providers.  Digital platforms can host multiple service providers, working to offer “end to end” services to drive transformation in agricultural markets and impact for smallholders, while decreasing risks and increasing revenue models for fintechs, agtechs and other market actors.

Drawing on Mercy Corps’ experience implementing the AgriFin Mobile, AgriFin Accelerate and AgriFin Digital Farmer programs, GIZ has engaged Mercy Corps to understand how young technology innovators can be supported in scale and operational viability by engaging with emerging models of digital platforms. The GIZDigital Agriculture Africa Phase 2 is a six-month, €1,300,000 initiative to work with a cohort of partners in Kenya and Nigeria to develop digital solutions that address challenges in the agriculture sector especially brought about by the Covid 19 pandemic. The COVID-19 pandemic has drawn attention to the complex fragility of many countries, highlighted most clearly in the interplay of public health, markets and food systems. Early warning signs are emerging that the continent is on the brink of an unprecedented food security crisis. In Kenya it is estimated that there are sufficient strategic reserves for three months, but disrupted food systems, logistics and evidence of food hoarding may shorten that timeline, particularly as the largest desert locust invasion in 70 years.

The World Bank estimates that the COVID-19 pandemic is likely to push upwards of 115 million into extreme poverty and set back poverty reduction by around three years.  The primary risks to food security at the country level include: disruptions in domestic food supply chains, other shocks affecting food production, and loss of incomes and remittances that have created strong tensions and food security risks in many countries. A number of countries are experiencing varying levels of food price inflation, at the retail level, due to measures taken to combat the spread of COVID-19. Higher retail prices, combined with reduced incomes, mean more and more households are having to cut down on the quantity and quality of their food consumption, with potentially lasting impacts on nutrition and health. The U.N. World Food Programme has warned that the number of people at risk of encountering acute food insecurity will come close to doubling at the end of the year, from the initial 135 million currently facing acute hunger.

Purpose of Engagement

This GIZ Digital Agriculture Africa (DAA) and smart development#SDFund aims to promote zero contact and prevent the spread of COVID-19 by utilizing technology to expand access to food, improve distribution of agriculture outputs by consumers through support farmers utilize updated agriculture extension information to bolster production, cultivation, marketing, and distribution of food in a number of geographies.

The objective of this engagement is to support Mercy Corps Agrifin’s vision for a sustainable Sprout, the Open Content Agriculture Platform. Through this engagement, the selected firm will support Sprout’s development of a detailed business and sustainability plan as global public good.

Scope of work

The contractor will engage with the AgriFin team, Sprout Project Team, and Sprout Platform partners:

- Support in developing business and sustainability plan for the Sprout Platform, to include identification of:

  - Review of Sprout platform’s existing and planned content providers, farmer facing organizations, partners and stakeholders, and funding organizations

  - Review of Sprout platform’s existing and planned content, services and products currently available, and make recommendations on other value-added services that content providers, farmer facing organizations, partners and stakeholders could leverage or benefit from Sprout.

  - Benchmark similar business models and industry trends

  - Review of Sprout platform’s existing and planned go-to-market strategies, including marketing and awareness, business development pipeline, and other

  - Develop a competitive assessment matrix of two competitor organizations and companies, highlighting key Sprout competitors. Competitive assessment matrix should also outline potential risks to sustainability of Sprout

  - Design of potential Sprout business model (including financial modeling) with associated vision, potential revenue, and income generation models, as well as key resource needs as path to sustainability

  - Highlight services that can be revenue generating, develop potential pricing models for revenue generating service, and provide recommendations on types of organizations the Sprout Platform should target (for revenue generation) through its progression and growth

  - Conduct a review and assessment of partners content and agriculture service/product needs to provide guidance and demand that their partners support developing revenue and income generation models.

  - Develop a pitch deck to support the Sprout Platform with investment and fundraising efforts.

Deliverables

The contractor will work to produce the following deliverables, in close collaboration with the AgriFin teams:

| Deliverable # | Deliverable Description | Estimated Deliverable Due Date |
| --- | --- | --- |
| Business and sustainability plan framing and outlining Report | Submit report detailing: -Outcome of review of Sprout platform’s existing and planned content providers, farmer facing organizations, partners and stakeholders, and funding organizations -outcome of review of Sprout platform’s existing and planned content, services, and products currently available, and make recommendations on other value-added services that content providers, farmer facing organizations, partners and stakeholders could leverage or benefit from Sprout. -outcome of review of Sprout platform’s existing and planned go-to-market strategies, including marketing and awareness, and BD pipeline - Competitive assessment matrix of sprout partner organizations and companies -Benchmark similar business models and industry trends | 20th Jan 2023 |
| Preliminary business and sustainability plan | -Conduct an assessment of partner’s content and agriculture service/product needs to provide guidance and demand for support by sprout partners and sprout’s income generation model - Develop potential Sprout business and sustainability model (including financial modeling) with associated vision, potential revenue, and income generation models, as well as key resource needs as path to sustainability and submit to Mercy Corps Agrifin for review -Develop sprout pitch decks for the sprout platform and submit to Mercy Corps Agrifin for review | 30th Jan 2023 |
| Final sprout business sustainability framework | -Submit final pitch decks after including inputs from Mercy Corps Agrifin to support the Sprout Platform with fundraising efforts. - Submit the final business and sustainability plan after factoring in inputs from Mercy Corps Agrifin. Business plan must include recommendations on types of organizations the Sprout Platform should target (for revenue generation) through its progression and growth | 13th Feb 2023 |  |

The consultancy will also submit regular invoices, as agreed tied to completion of deliverables.

Required Qualifications

The contractor must have a strong track record in partnership development and sustainable business model development.

- The contractor should have demonstrable experience developing business plans, organizational change management approaches and roadmaps for similarly complex digital platforms for agriculture involving financial services, market access, smart farming and other innovations in the East and Southern African context, as well as a deep understanding of smallholder farmer needs across this region.

Furthermore:

- The contractor should be able to operate in the region as per this scope of work with excellent in-country networks where applicable

- Able to lead technical services in all areas listed under the Scope of Work, to include expertise in digital financial services, business strategy and modeling, human centered design, agriculture, monitoring and evaluation, partnership development, public learning formulation and project management and coordination.

- Given this is a complex program requiring multi-stakeholder engagement and expertise, we are looking for an experienced contractor with demonstrable capacity to manage a large project of this nature and which can demonstrate a successful track record with Mercy Corps and programming similar to AgriFin

Ownership/Control of Work Product/Publication

Matters relating to ownership and control of work product and publication of materials produced during course of this engagement will be addressed in the contract

Authorship and Acknowledgement

Matters relating to authorship and acknowledgment of any materials produced by the contractor during the course of this engagement are addressed in the main contract agreement entered into between Mercy Corps and the Contractor for performance of services for AgriFin programming.

Task Manager/Reporting

Task Manager is D-CSA and Sprout Platform Lead with assistance of Sprout Platform Product Lead, and  Mercy Corps AgriFin Program Director. Program Director has final sign-off on deliverables and invoices.

Payment and Schedule

Payment will be made upon regular invoicing against satisfactory delivery and acceptance of services rendered as a result of this consultancy.

IFAD, Smallholders, food security, and the environment, 2013

IFAD, “Sub-Saharan Africa: The state of smallholders in agriculture”, Schonberger and Delaney 2011.

Peck, Anderson, “Segmentation of Smallholder Households: Meeting the Range of Financial Needs in Agricultural Families”, CGAP Focus Note #85, April 2013.

Dalberg, 2013

Dalberg, 2013

MasterCard Foundation, “Inflection Point: Unlocking growth in the era of farmer finance”, April 2016

Dalberg, 2013

https://blogs.worldbank.org/opendata/updated-estimates-impact-covid-19-global-poverty-effect-new-data

https://www.worldbank.org/en/topic/agriculture/brief/food-security-and-covid-19